## Sheet1
Day | Time | Work I did
2021-10-22 | 3:10 - 3:54 PM | Tinkering with the program, added lenoir as a test.
2021-10-24 | 7:20 - 7:50 PM | Miscellanous coding
2021-10-26 | 1:40 - 1:54 PM | Miscellanous coding
2021-11-04 | 10:50 - 11:01 PM | Miscellanous coding
2021-11-11 | 2:10 - 2:56 PM | Miscellanous coding
2021-11-29 | 2:56 - 3:32 PM | Miscellanous coding
2021-11-29 | 6:18 - 6:31 PM | Miscellanous coding
2021-11-29 | 11:53 - 12:28 AM | Miscellanous coding
2021-11-30 | 7:41 AM - 9:36 AM | Miscellanous coding
2021-11-30 | 7:52 PM - 9:09 PM | Added an Inventory command
2021-12-01 | 7:40 - 7:55 AM | Worked on adding items to rooms that can be picked up.
2021-12-01 | 4:16 - 6:28 PM | Made items too heavy for the player. Got done with inventory command. You can now win the game. Added a room where you can win.
2021-12-02 | 8:30 - 9:55 PM | Worked on BackCommand, close to full implementation
2021-12-03 | 10:10 - 10:40AM | Changing room names and adding more rooms.
2021-12-03 | 4:18 - 4:45PM | Rearranging the map, you can now leave the winning room.
2021-12-04 | 9:51 - 11:06 AM | Added more rooms and connected them to each other. Cleaned up code.
2021-12-04 | 5:44 - 7:30PM | Added notes into specific rooms. Updated inventory to include its long name instead of the short name.
2021-12-05 | 8:25 - 9:37 AM | Added fake notes into my world. Changed intro of game. Now only have three tries at the win room.
2021-12-05 | 10:00 - 11: 47 AM | Added all of the notes into rooms. Renamed notes to notes with different numbers.
2021-12-05 | 1:00 - 3:46 PM | Rearranging the rooms in according to my map. Displayed how many tries you have in the room of winners. Adding all relevant comments.